## 2027 Sequenced Plan
2027 Remediation Plan — the 23 open items sequenced, plus the recertification gates
MercyBridge Health Network — HIPAA Security Program · Phase 09 · Illustrative Portfolio Sample
Due | ID | Item | Owner | Depends on | Critical path | Funding
2027-01-31 | CAP-03 / IA-F-05 / D-3 | SIEM onboarding for the final 3 of 68 ePHI systems | Marcus Reed | Vendor log-export capability on two hosted systems | CP | Funded
2027-01-31 | IA-F-02 | Activity-review attestation enforced in the GRC workflow | Marcus Reed | Two completed review cycles to evidence | — | Funded
2027-01-31 | IA-F-06 | Procedural-dependency field in change control | Karen Boyd | None — deployed, evidence period running | — | Funded
2027-01-31 | IA-F-08 | Disposal certificate upload as a mandatory closure step | Anthony Ruiz | Ticket workflow release | — | Funded
2027-02-28 | M-2 | Joint full-scale restoration test with Halcyon Health | Anthony Ruiz | Halcyon window — outside MercyBridge's control. Already re-baselined once; no second re-baseline authorised | CP | Funded
2027-02-28 | CAP-04 / IA-F-07 | Provisioning approval capture with the manual bypass disabled | Marcus Reed | Operating period since 2026-12-11 | CP | Funded
2027-02-28 | CAP-08 / IA-F-04 | Ambulatory physical consistency — quarterly alarm testing, electronic visitor logging | Facilities Director | Procurement complete; installation at two paper sites | CP | Funded
2027-02-28 | IA-F-09 | Break-glass review-due alerting to the CMIO office | Dr. Samuel Ortega | Alerting build | — | Funded
2027-02-28 | D-14 | Detect-to-escalate median from 41 minutes to under 30 | Marcus Reed | Triage automation; CAP-03 completion improves the input | — | Funded
2027-03-31 | CAP-01 / R-47a | Validated 24-hour restoration for the remaining 5 of 12 Tier 1 systems | Anthony Ruiz | M-2 | CP | Funded
2027-03-31 | CAP-07 / IA-F-01 | HR-to-IAM automation for per-diem and affiliated worker types | Marcus Reed / HR Director | HR system per-diem feed | CP | Funded
2027-03-31 | F-2a | Read-only clinical viewer at the remaining 4 outpatient sites | Ambulatory Director | Site network readiness | — | Funded
2027-03-31 | O-6 | Customer-managed encryption keys at Halcyon | Lisa Coleman / Daniel Cho | Contract amendment — vendor dependent | — | Requested
Q1 2027 | V-24 | Immutable or offline copies for the remaining 3 of 9 Tier 2–3 systems | Anthony Ruiz | Capital release | — | Requested
Q1 2027 | MIN-1 | Mailbox ePHI minimisation from INC-2026-0044 | Rebecca Stern | Scope agreed; clinical consultation | — | Funded
2027-04-30 | CAP-02 / IA-F-03 | BA monitoring and Sec.164.314(a)(2)(iii) flow-down below the critical tier — ~118 of ~180 remaining | Lisa Coleman | Tiering model approved 2026-12-05; portal build; 1.0 incremental FTE | CP | Requested
2027-06-30 | CAP-05 | Retire or replace the legacy wireless PSK remnant — 173 of 214 devices remaining | Anthony Ruiz | Device replacement lead time; capital | CP | Part-funded
2027-06-30 | CAP-06 | Vendor-supported assessment path or replacement for 54 of 72 unassessable hosts | Anthony Ruiz | Vendor agreement — 18 of 72 agreed to date | CP | Requested
2027-06-30 | *R-41 condition* | Second consecutive clean IV-05 reconciliation | Marcus Reed | Two clean quarters — cannot be accelerated | — | Funded
2027-07-15 | Recert gate | Internal readiness review and evidence freeze | Daniel Cho | All eight CAPs closed and evidenced | CP | Funded
2027-08-02 | Recert | Beacon Assurance validation fieldwork opens | Daniel Cho | Engagement letter by 2027-04-30 | CP | Funded
2027-09 | A-03 | Annual independent penetration test — full scope, Ironwood | Marcus Reed | None | — | Funded
2027-09-30 | Recert | Submission to HITRUST for quality review | Daniel Cho | Fieldwork closed | CP | Funded
2027-11-29 | Certificate expiry | Recertification must be issued by this date | Daniel Cho | HITRUST QA cycle | CP | —
Q2 2027 | IA follow-up | Internal audit verification of all 9 recommendations | Priya Anand | Recommendation closures | — | Funded
2027-12 | A-12 | Board report on the 2027 position | Daniel Cho | Annual cycle complete | — | Funded

## Open Item Ageing
Ageing of the 23 Open Items at 2026-12-31
MercyBridge Health Network — HIPAA Security Program · Phase 09 · Illustrative Portfolio Sample
Bucket | Items | Note
Overdue | 1 | M-2 — the joint Halcyon restoration test. Re-baselined once to 2027-02-28. A second slip goes to the Board with a recovery plan, not a new date
Due 2027-01-31 | 5 | CAP-03 / IA-F-05, IA-F-02, IA-F-06, IA-F-08 — SIEM completion and evidence-workflow items
Due 2027-02-28 | 6 | CAP-04 / IA-F-07, CAP-08 / IA-F-04, IA-F-09, D-14 — plus M-2 itself
Due 2027-03-31 | 5 | CAP-01 (depends on M-2), CAP-07 / IA-F-01, F-2a, O-6
Due 2027-04-30 | 2 | CAP-02 / IA-F-03 — business associate monitoring below the critical tier
Due 2027-06-30 | 2 | CAP-05 legacy wireless, CAP-06 unassessable hosts — both capital or vendor dependent
Q1 2027, no fixed date | 2 | V-24 Tier 2-3 immutability, MIN-1 mailbox minimisation
Open beyond 2027-11-29 recertification | 0 | No open item is scheduled past the certificate expiry

## 2027 Budget
Indicative 2027 Budget — dates without funded owners are wishes
MercyBridge Health Network — HIPAA Security Program · Phase 09 · Illustrative Portfolio Sample
Workstream | Indicative cost | Type | Funding status
Restoration validation, joint vendor test, DR tooling (M-2, CAP-01, V-24) | $420K | Operating + capital | Funded
SIEM completion, detection engineering, triage automation (CAP-03, D-14) | $310K | Operating | Funded
Legacy wireless retirement — 173 devices (CAP-05) | $560K | Capital | Part-funded — $310K approved, $250K requested
Unassessable host assessment path or replacement — 54 hosts (CAP-06) | $480K | Capital | Requested
HR-to-IAM automation and provisioning controls (CAP-07, CAP-04, IA-F-01/07) | $180K | Operating | Funded
BA monitoring platform and 1.0 incremental FTE (CAP-02, IA-F-03) | $240K | Operating | Requested
Ambulatory physical consistency (CAP-08, IA-F-04) | $195K | Capital | Funded
Evidence automation from 64% to 80% | $150K | Operating | Requested
HITRUST rapid recertification — Beacon fees, MyCSF, internal effort | $265K | Operating | Funded
Annual penetration test and quarterly purple team (Ironwood) | $95K | Operating | Funded
Contingency at 10% | $290K | — | Requested
2027 TOTAL | ~$3.19M | — | ~$2.05M funded · ~$1.14M requested