## High Risk Treatment
High-Risk Treatment Plan — §164.308(a)(1)(ii)(B) risk management (11 High risks)
MercyBridge Health Network — HIPAA Security Risk Analysis §164.308(a)(1)(ii)(A) ¦ 56 risks: 11 High · 27 Moderate · 18 Low ¦ posture Moderate ¦ Confidential — ePHI // Illustrative
Risk ID | Risk (abridged) | Score | Treatment | Remediation Wave | Target Residual | Owner | Delivered in Phase
R-01 | Credential compromise yields unauthorised ePHI access because MFA is enforced on only 44 o… | 16 | Mitigate | Wave 1 | Moderate or below | Marcus Reed | 04 / 05
R-02 | Shared and generic clinical logins defeat unique user identification and destroy audit att… | 16 | Mitigate | Wave 1 | Moderate or below | Marcus Reed | 04
R-09 | Known exploited vulnerabilities on 1,300 unsupported-OS devices cannot be patched | 16 | Mitigate | Wave 1 | Moderate or below | Anthony Ruiz | 05
R-10 | Malware propagation into device VLANs halts clinical device availability — patient-safety … | 15 | Mitigate | Wave 1 | Moderate or below | Anthony Ruiz | 05
R-11 | ePHI at rest on 3,170 ePHI-bearing devices cannot be encrypted; loss or disposal forfeits … | 15 | Mitigate | Wave 2 | Moderate or below | Anthony Ruiz | 05
R-17 | Incomplete micro-segmentation (41 of 68 systems) permits lateral movement into Tier 1 clin… | 16 | Mitigate | Wave 2 | Moderate or below | Anthony Ruiz | 05
R-23 | Enterprise ransomware encrypts Tier 1 clinical systems, causing multi-day care disruption … | 20 | Mitigate | Wave 2 | Moderate or below | Daniel Cho | 06
R-24 | Double-extortion exfiltration of ePHI before encryption triggers presumptive breach and ma… | 16 | Mitigate | Wave 2 | Moderate or below | Daniel Cho | 07
R-28 | Compromise or extended outage of the vendor-hosted Halcyon EHR holding the entire 2.1M-rec… | 15 | Mitigate | Wave 3 | Moderate or below | Daniel Cho | 05
R-34 | Phishing or business email compromise gives an adversary a workforce mailbox containing eP… | 15 | Mitigate | Wave 3 | Moderate or below | Daniel Cho | 05
R-40 | ePHI at rest is unencrypted or partially encrypted on 17 of 68 systems and on parts of the… | 16 | Mitigate | Wave 3 | Moderate or below | Daniel Cho | 07