## Control-Risk Trace
Control-to-Risk Traceability — R-28 closes; register reaches 0 High
MercyBridge Health Network — Business Associate & Third-Party Risk ¦ ~180 BAs · 24 critical/high · BAA coverage 47 of 47 ¦ Confidential — ePHI // Illustrative
Risk ID | Risk | Entering | Controls Applied | Residual | Note
R-28 | Compromise or extended outage of the vendor-hosted Halcyon EHR (2.1M records) | High (15) | Nine-measure concentration plan: independent ePHI export, tested exit path, enhanced contractual terms, assurance beyond documentary, joint incident exercise, key-custody escalation, SLA and RTO commitments, downstream mapping, executive escalation route | Moderate (10) | Impact floored at 5 by ESC-2; likelihood reduced 3 → 2
R-29 | Business associate operating without a current or adequate BAA | Moderate (12) | All three remediations closed; coverage 47 of 47; 2026 template with flow-down | Moderate (8) | Monitored at renewal
R-30 | Unmapped subcontractor chain beneath critical business associates | Moderate (9) | Disclosure campaign 15 → 24 of 24; 71 downstream entities registered incl. 9 fourth parties | Low (6) | Nine unmapped chains closed
R-31 | Business associate breach discovered late through the notification chain | Moderate (8) | Contractual 5-day notification; 24/7 intake; joint investigation protocol | Moderate (8) | Carried — depends on BA behaviour
R-32 | Offshore subcontracting without disclosure or flow-down | Low (4) | Disclosure obligation; two offshore services identified and governed | Low (2) | Closed
R-33 | PHI retained by a business associate after termination | Low (4) | Return-or-destroy with certificate; 7 of 7 terminations certified | Low (2) | Closed

## Register Position
Register Position Across All 56 Risks
MercyBridge Health Network — Business Associate & Third-Party Risk ¦ ~180 BAs · 24 critical/high · BAA coverage 47 of 47 ¦ Confidential — ePHI // Illustrative
Point | High | Moderate | Low | Posture
Entering Phase 06 | 1 | 20 | 35 | Low-to-Moderate
Leaving Phase 06 | 0 | 20 | 36 | Low-to-Moderate — first position with no High risk