## Control-Risk Trace
Control-to-Risk Traceability — independent assessment validates, and where testing disproved an assumption, raises
MercyBridge Health Network — Independent Assessment & Audit Readiness ¦ pen test 16 findings remediated · internal audit Satisfactory · HITRUST i1 certified ¦ Confidential — ePHI // Illustrative
Risk ID | Risk | Entering | Lens | Evidence | Residual | Movement | Rating
R-02 | Shared and generic logins defeat unique identification and destroy audit attribution | 2 × 4 = 8 | Pen test · Audit | PT-02 found a shared vendor service credential in use across 11 imaging modalities since 2022. Remediated, per-engineer accounts issued, broker mandated (IV-08); Ironwood retest pass | 2 × 4 = 8 | HELD — the class was proven to still exist; one retest is not an operating history | Moderate
R-06 | Vendor remote-support entitlements across the device estate are under-reviewed | 2 × 4 = 8 | Pen test · Audit · HITRUST | PT-02 root cause; broker mandate now covers all third-party remote support across ~180 BAs; session recording live; HITRUST Third Party Assurance 86% with CAP-02 open | 2 × 4 = 8 | HELD — CAP-02 shows oversight below the critical tier is still thin | Moderate
R-09 | Known exploited vulnerabilities on unsupported-OS devices cannot be patched | 2 × 4 = 8 | Vuln · HITRUST | KEV-listed instances reduced 148 → 0 (100%); monthly authenticated scanning at 96.2%; compensating packages evidenced (IV-04) | 2 × 4 = 8 | VALIDATED — the residual is structural, not remediable; the score was already honest | High
R-10 | Malware propagation into device VLANs halts clinical device availability (ESC-1) | 2 × 4 = 8 | Pen test · HITRUST | PT-01 proved the boundary was not what MercyBridge believed — 412 legacy devices reachable from the workstation VLAN via a 2019 static route and a 2024 ACL rule. Remediated; default-deny rebuilt; IV-07 quarterly validation introduced | 2 × 4 = 8 | HELD — the fix is verified; the *process* that let the boundary rot needs two clean quarterly validations before the score moves | Moderate
R-11 | ePHI at rest on device platforms that cannot encrypt; loss forfeits safe harbour (ESC-1) | 2 × 5 = 10 | Pen test · Audit · HITRUST | Ironwood recovered no plaintext ePHI from any reached storage; 68 of 68 systems encrypted; the device population remains structurally unencryptable | 2 × 5 = 10 | VALIDATED — unchanged and correctly stated | High
R-12 | Devices without an MDS2 on file cannot be assessed to a consistent standard | 2 × 4 = 8 | Vuln · HITRUST | Passive attribution at 5,704 of 6,120 (93.2%); procurement clause added; CAP-06 open on 72 hosts that cannot accept credentialed assessment | 2 × 4 = 8 | HELD — CAP-06 dated 2027-06-30 | Moderate
R-17 | Incomplete micro-segmentation permits lateral movement into Tier 1 clinical systems | 2 × 4 = 8 | Pen test · Audit · HITRUST | The definitive test of this risk. PT-01 crossed a boundary that was documented as closed; PT-06 and PT-08 showed lateral paths on the workstation tier. All remediated and retested; Domain Administrator not obtained; tiered administration held; Network Protection domain 93% | 2 × 4 = 8 | HELD — segmentation is now proven in one direction and disproven in another. IV-06 and IV-07 are the treatment; their evidence is quarterly | Moderate
R-23 | Enterprise ransomware disabling Tier 1 clinical systems across 4 hospitals and ~30 clinics (ESC-2) | 2 × 4 = 8 *(conditional)* | Pen test · Audit · HITRUST | Immutable copies verified; but the joint Halcyon restoration test (M-2) slipped from 2026-09 into 2027-02, so recoverability at enterprise scale is unproven. HITRUST BC/DR domain 79%, the lowest in the assessment, with CAP-01 at 25% | 2 × 5 = 10 | RAISED — the conditional claim lapsed exactly as 07.11 said it would | High
R-24 | Double-extortion exfiltration of ePHI before encryption | 3 × 3 = 9 | Pen test · Audit · HITRUST | Detection rate against tester actions 48% → 74% after IV-09; D-12 and D-13 closed; egress baselining and leak-site monitoring operating; Incident Management domain 100%; Ironwood extracted no data at any point | 3 × 3 → 2 × 4 = 8 | REDUCED within band — likelihood down on measured detection, impact held | High
R-28 | Compromise or extended outage of the vendor-hosted Halcyon EHR holding 2.1M records (ESC-2) | 2 × 5 = 10 | Audit · HITRUST | SOC 2 Type II relied upon after scope and competence review; MercyBridge-side interfaces tested clean; O-6 customer-managed keys still open; the joint restoration test is also the Halcyon dependency | 2 × 5 = 10 | VALIDATED — and explicitly not reduced while O-6 and M-2 are open | Moderate
R-30 | Subcontractor (BA-of-BA) chain is not visible for hosted services | 2 × 4 = 8 | Audit · HITRUST | IA-F-03: 3 of 40 sampled BAAs lacked §164.314(a)(2)(iii) flow-down language; CAP-02 on monitoring below the critical tier | 2 × 4 = 8 | HELD — two independent lenses found the same thin layer | High
R-35 | Extended adversary dwell time because telemetry does not reach the SIEM | 2 × 4 = 8 | Pen test · Audit · HITRUST | The pen test measured what the register had estimated: 48% detection, 41-minute median escalation, PT-02 and PT-03 undetected. Improvements landed (74% re-measure) but 6 of 68 systems still do not forward logs; Audit Logging domain 82% | 2 × 4 = 8 | HELD — improved but not closed; moves on SIEM completion, not on one purple-team run | High
R-36 | Workforce browses records without a treatment, payment or operations purpose | 2 × 4 = 8 | Audit | IA-F-02: activity review performed but the reviewer attestation was not retained for 3 of 25 sampled months. The control operates; the evidence of it does not always survive | 2 × 4 = 8 | HELD — a detective control you cannot evidence is not a detective control an assessor will credit | Moderate
R-43 | Integrity loss on post-downtime documentation reconciliation (ESC-3) | 3 × 3 = 9 | Audit | F-3 closed 2026-11-20: HIM surge model re-based on a 10-day outage, agency surge contract executed, and Internal Audit verified the closure. This is the assumption TTX-2026-01 disproved in Phase 07, now corrected with evidence | 2 × 3 = 6 | REDUCED — Moderate → LOW | Moderate
R-47 | Tier 1 restoration time has never been validated at full scale | 2 × 4 = 8 | Audit · HITRUST | The validation count did not move: 12 of 12 documented, 7 of 12 validated. CAP-01 scored 25%, the lowest single requirement score in the i1 assessment | 2 × 4 = 8 | HELD — and it is the register's most exposed position | High
R-48 | Backup immutability and offline copies incomplete for Tier 2–3 systems | 2 × 4 = 8 | Audit · HITRUST | V-24: 6 of 9 remaining systems complete; backup network isolated and not reachable or alterable from any position Ironwood achieved | 2 × 4 = 8 | HELD — closes on the remaining 3 in Q1 2027 | Moderate
R-41 | Unstructured and unaccounted ePHI outside the governed inventory | 2 × 3 = 6 (Low) | Pen test (PT-03) | PT-03. An internet-facing appointment application, live since 2018, superseded in 2023, never decommissioned, holding 6,880 records of name, date of birth, contact details and free-text reason-for-visit. It appeared in no ePHI inventory, had no owner, no BAA dependency, no patching path and no logging. The Low residual rested on the assumption that discovery scanning had bounded the sprawl. It had not | 2 × 4 = 8 | RAISED — Low → MODERATE | Moderate

## Register Position
Register Position Across All 56 Risks
MercyBridge Health Network — Independent Assessment & Audit Readiness ¦ pen test 16 findings remediated · internal audit Satisfactory · HITRUST i1 certified ¦ Confidential — ePHI // Illustrative
Point | High | Moderate | Low | Note
Entering Phase 08 | 0 | 16 | 40 | Low-to-Moderate
Leaving Phase 08 | 0 | 16 | 40 | Same totals, different composition — 2 reduced, 2 raised