## Milestones
Assessment Roadmap & Milestones (~11 months)
MercyBridge Health Network — HIPAA Security Program ¦ HHS OCR ¦ NIST SP 800-66 Rev.2 · HITRUST CSF ¦ Confidential — ePHI // Illustrative
Milestone | Phase | Target | Owner | Status
Program kickoff | 01 | 2026-02-02 | Cho | Complete
Foundation & scoping baselined | 01 | 2026-02 | Cho | Complete
ePHI inventory & data-flow mapping | 02 | 2026-03 | Reed | Complete
HIPAA risk analysis complete | 03 | 2026-04 | Cho | Complete
Administrative safeguards & policies | 04 | 2026-06 | Cho | Complete
Physical & technical safeguards | 05 | 2026-07 | Reed | Complete
BAA remediation complete | 06 | 2026-07 | Coleman | Complete
IR plan + tabletop | 07 | 2026-08 | Cho | Complete
Penetration test | 08 | 2026-09 | Anand | Complete
HITRUST i1 validated assessment | 08 | 2026-11 | Cho | Complete
Board report & program review | 09 | 2026-12 | Cho | Complete