## Control-Risk Trace
Control-to-Risk Traceability — 31 of 56 risks treated by administrative safeguards
MercyBridge Health Network — Administrative Safeguards §164.308 ¦ 9 standards · 21 implementation specifications ¦ 15 of 24 policies ¦ Confidential — ePHI // Illustrative
Risk ID | Entering Rating | Risk | Standard / Spec | Phase 04 Instrument | Policy | Residual | Onward Treatment
R-02 | High (16) | Shared / generic clinical logins destroy audit attribution | §164.308(a)(3)(ii)(A)–(B); (a)(1)(ii)(C)–(D) | 04.04 authorisation and clearance; named-account remediation; sanction exposure | POL-05, POL-03, POL-04 | Moderate (12) | Technical unique user ID §164.312(a)(2)(i) — Phase 05, Wave 1
R-10 | High (15) | Malware into device VLANs halts clinical devices (ESC-1) | §164.308(a)(7)(i)–(ii)(A)–(E) | 04.08 criticality analysis, emergency mode operation, device downtime procedures | POL-13 | High (15) — consequence managed, likelihood unchanged | Micro-segmentation and device lifecycle — Phase 05, Wave 3
R-23 | High (20) | Enterprise ransomware encrypts Tier 1 clinical systems (ESC-2) | §164.308(a)(6)(ii); (a)(7)(ii)(A)–(D) | 04.07 SEV-1 path; 04.08 immutable backup, clean-build recovery, full-scale restoration test | POL-12, POL-13 | High (15) | EDR, segmentation — Phase 05, Wave 1
R-24 | High (16) | Double-extortion exfiltration before encryption | §164.308(a)(6)(ii) | 04.07 detection, scoping and 4-factor interface | POL-12 | High (16) | Encryption at rest and DLP — Phase 05, Wave 2 (attributed there)
R-28 | High (15) | Halcyon EHR compromise or extended outage — 2.1M records (ESC-2) | §164.308(b)(1); (a)(7)(ii)(C) | 04.10 BAA security, DR and notification clauses; 04.08 hosted-EHR downtime procedures | POL-15, POL-13 | High (15) | Tested BA assurance — Phase 06; Wave 3
R-34 | High (15) | Phishing / BEC compromises mailboxes containing ePHI | §164.308(a)(5)(i)–(ii)(A)–(D) | 04.06 training to 100%, phishing simulation, reporting culture, reminders | POL-09, POL-11 | Moderate (9) | MFA (R-01) — Phase 05, Wave 1
R-03 | Moderate (12) | 214 standing elevated EHR accounts | §164.308(a)(4)(ii)(B)–(C); (a)(3)(ii)(A) | 04.05 least privilege, quarterly recertification; 04.04 authorisation | POL-06, POL-07 | Moderate (8) | Privileged access tooling — Phase 05
R-04 | Moderate (12) | Access retained >24h after departure or transfer | §164.308(a)(3)(ii)(C) | 04.04 joiner–mover–leaver SLA, automated deprovisioning, exception log | POL-05 | Low (6) | Closed in Phase 04; monitored quarterly
R-05 | Moderate (9) | Break-glass used without retrospective review | §164.308(a)(4)(ii)(B); (a)(1)(ii)(D) | 04.05 break-the-glass workflow; 100% retrospective review within 72h | POL-08, POL-04 | Low (6) | Emergency access procedure §164.312(a)(2)(ii) — Phase 05
R-06 | Moderate (8) | 742 devices with under-reviewed vendor remote support | §164.308(a)(4)(ii)(B)–(C); (b)(1) | 04.05 vendor entitlement review; 04.10 contractual access limits | POL-06, POL-15 | Moderate (8) | NAC and session brokering — Phase 05; monitoring — Phase 06
R-08 | Low (4) | Patient-portal proxy relationships not recertified | §164.308(a)(4)(ii)(C) | 04.05 proxy recertification cycle | POL-06 | Low (2) | Closed in Phase 04
R-26 | Moderate (9) | Macro / script initial access from email attachments | §164.308(a)(5)(ii)(B); (a)(6)(ii) | 04.06 malicious-software protection and simulation; 04.07 reporting | POL-10, POL-09 | Low (6) | EDR coverage (R-25) — Phase 05
R-31 | Moderate (8) | BA breach notice too late for the 60-day duty | §164.308(b)(1); (a)(6)(ii) | 04.10 five-day contractual notice clock; 04.07 intake path | POL-15, POL-12 | Moderate (8) | BA monitoring — Phase 06; notification — Phase 07
R-32 | Low (6) | Offshore support access exceeds minimum necessary | §164.308(a)(4); (b)(1) | 04.05 minimum necessary; 04.10 data-set reduction clause | POL-07, POL-15 | Low (6) | Offshore access review — Phase 06
R-35 | Moderate (12) | Misdirected fax, email, statement or records release | §164.308(a)(5)(i)–(ii)(A) | 04.06 targeted training, recipient verification, reminders | POL-09, POL-07 | Moderate (9) | Outbound DLP — Phase 05
R-36 | Moderate (12) | Workforce browses records without a TPO purpose | §164.308(a)(1)(ii)(C)–(D); (a)(4); (a)(8) | 04.02 activity review across all 68 systems and sanction linkage; 04.09 evaluation | POL-04, POL-03, POL-07 | Moderate (8) | Audit controls §164.312(b) — Phase 05
R-37 | Moderate (9) | 91% training completion; thin role-based clinical content | §164.308(a)(5)(i) | 04.06 role-based tracks, clinician curriculum, 100% completion standard | POL-09 | Low (4) | Closed in Phase 04; measured quarterly
R-38 | Low (6) | Unsanctioned messaging apps carry clinical information | §164.308(a)(5)(ii)(A); §164.316(a) | 04.06 reminders and sanctioned-channel guidance; 04.11 policy currency | POL-09, POL-01 | Low (4) | Transmission security §164.312(e) — Phase 05
R-39 | Low (4) | Service desk social-engineered into a credential reset | §164.308(a)(3)(ii)(A); (a)(5)(ii)(D) | 04.04 identity verification protocol; 04.06 service-desk training | POL-05, POL-11 | Low (2) | Closed in Phase 04
R-43 | Moderate (9) | Clinical data integrity degraded — wrong-patient, duplicates, interface corruption (ESC-3) | §164.308(a)(7)(ii)(E); (a)(1)(ii)(D) | 04.08 applications and data criticality analysis; downtime reconciliation | POL-13, POL-04 | Moderate (9) | Integrity controls §164.312(c)(1) — Phase 05
R-46 | Low (4) | Incidental ePHI in logs, SIEM and non-production | §164.308(a)(6)(ii); (a)(1)(ii)(D) | 04.07 handling rules for evidence containing ePHI | POL-12, POL-04 | Low (4) | Non-production data handling — Phase 05
R-47 | Moderate (12) | Tier 1 restoration time never validated at full scale | §164.308(a)(7)(ii)(A)–(D) | 04.08 full-scale restoration test, RTO/RPO validation, after-action report | POL-13 | Moderate (8) | Retested annually under 04.09
R-48 | Moderate (8) | Backup immutability incomplete for nine Tier 2–3 systems | §164.308(a)(7)(ii)(A) | 04.08 backup standard, immutability requirement, dated remediation tickets | POL-13 | Moderate (8) | Wave 2 — 2027-01-31
R-49 | Moderate (9) | Downtime procedures unexercised at ~30 outpatient sites | §164.308(a)(7)(ii)(C)–(D) | 04.08 site downtime exercises, downtime kits, kit inspection log | POL-13 | Low (6) | Rolling three-year site exercise cycle
R-50 | Low (6) | Single-path connectivity at four outpatient sites | §164.308(a)(7)(ii)(C) | 04.08 emergency mode operation for isolated sites | POL-13 | Low (6) | Carrier diversity — FY2027 capital
R-51 | Moderate (9) | Unattended logged-in workstations in clinical areas | §164.308(a)(5)(ii)(A) | 04.06 security reminders, clinical area campaign, observation rounds | POL-09 | Moderate (9) | Automatic logoff §164.312(a)(2)(iii); workstation security §164.310(b)–(c) — Phase 05
R-52 | Low (6) | Tailgating and badge-sharing into clinical space and IDFs | §164.308(a)(3)(ii)(A)–(B); (a)(5)(ii)(A) | 04.04 clearance and supervision; 04.06 awareness | POL-05, POL-09 | Low (6) | Facility access controls §164.310(a)(1) — Phase 05
R-53 | Low (4) | Flood, fire or extended power loss disables a site | §164.308(a)(7)(i)–(ii)(B) | 04.08 disaster recovery plan and site failover | POL-13 | Low (4) | Facility and environmental controls §164.310(a)(2) — Phase 05
R-54 | Moderate (9) | Legacy policy suite; §164.316(b) retention unevidenced | §164.316(a)–(b); (a)(1); (a)(2); (a)(8) | 04.11 24-policy suite, retention schedule, review cycle; 04.03 governance | POL-01, POL-14 | Low (6) | Closes when POL-16 … POL-24 are approved in Phase 05
R-55 | Low (6) | Activity review not evidenced for 19 systems | §164.308(a)(1)(ii)(D); (a)(8) | 04.02 activity review runbook extended to all 68 systems; 04.09 evaluation | POL-04, POL-14 | Low (4) | Audit controls §164.312(b) log fidelity — Phase 05
R-56 | Low (4) | Sanction application not consistently documented | §164.308(a)(1)(ii)(C); (a)(2) | 04.02 sanction register, tiered matrix, HR reconciliation; 04.03 ownership | POL-03 | Low (2) | Closed in Phase 04